# V.E.R.A.

Verified Existence and Reason Architecture

# Risk Register

TOGAF ADM Phase B: Business Architecture

Version 1.0 | January 2026

# Document Control

| Document Title | V.E.R.A. Risk Register |
| --- | --- |
| Version | 1.0 |
| Status | DRAFT |
| Date | January 28, 2026 |
| Author | Andreas Hamberger, M.A., AMinstD, IAPP, TOGAF |

# Executive Summary

This document identifies, assesses, and provides mitigation strategies for risks to the V.E.R.A. project. Risks are categorized by type (Technical, Knowledge, Project, External) and scored by likelihood × impact.

# 1. Risk Assessment Framework

## 1.1 Likelihood Scale

| Score | Rating | Description |
| --- | --- | --- |
| 1 | Rare | < 10% probability |
| 2 | Unlikely | 10-25% probability |
| 3 | Possible | 25-50% probability |
| 4 | Likely | 50-75% probability |
| 5 | Almost Certain | > 75% probability |

## 1.2 Impact Scale

| Score | Rating | Description |
| --- | --- | --- |
| 1 | Negligible | Minimal effect on project objectives |
| 2 | Minor | Some delay or minor rework required |
| 3 | Moderate | Significant delay or scope reduction |
| 4 | Major | Threatens key project objectives |
| 5 | Severe | Project failure or fundamental rethink |

## 1.3 Risk Score Matrix

Risk Score = Likelihood × Impact

• HIGH: Score 12-25 (Red) — Immediate action required

• MEDIUM: Score 6-11 (Amber) — Active monitoring and mitigation

• LOW: Score 1-5 (Green) — Standard tracking

# 2. Technical Risks

| ID | Risk | Description | L | I | Score | Rating | Mitigation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RSK-T01 | NTP Rule Complexity | R1-R9 implementation more complex than anticipated | 3 | 4 | 12 | HIGH | Incremental development; extensive unit testing; domain expert review |
| RSK-T02 | Parser Accuracy | NL to NTP conversion unreliable for complex sentences | 3 | 3 | 9 | MEDIUM | Start with structured input; iterative improvement; fallback to refusal |
| RSK-T03 | Performance at Scale | E! Corpus queries degrade at 10M+ entities | 2 | 3 | 6 | MEDIUM | Database indexing; caching; query optimization; load testing |
| RSK-T04 | LLM Response Variability | Claude outputs inconsistent, breaking verification | 2 | 3 | 6 | MEDIUM | Structured prompts; temperature control; validation layer |
| RSK-T05 | D-Service Edge Cases | Identity resolution fails on paradoxical cases | 3 | 3 | 9 | MEDIUM | Poincaré Paradox test suite; edge case documentation |

# 3. Knowledge Risks

| ID | Risk | Description | L | I | Score | Rating | Mitigation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RSK-K01 | Missing Source Material | Wessel 1989/1996 unavailable or inaccessible | 3 | 4 | 12 | HIGH | Proceed with validated 1992 content; defer unvalidated features; academic library search |
| RSK-K02 | Source Interpretation | Ambiguity in translating German logic to code | 2 | 3 | 6 | MEDIUM | Document interpretation decisions; domain expert approval; peer review |
| RSK-K03 | Domain Expert Availability | Andreas unavailable for extended periods | 1 | 4 | 4 | LOW | Document all decisions thoroughly; asynchronous communication; maintain decision log |

# 4. Project Risks

| ID | Risk | Description | L | I | Score | Rating | Mitigation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RSK-P01 | Scope Creep | Feature additions delay MVP beyond 12 weeks | 4 | 3 | 12 | HIGH | Strict MVP definition; backlog management; change control process |
| RSK-P02 | Resource Constraints | Insufficient development capacity for timeline | 3 | 3 | 9 | MEDIUM | Vibe coding approach; prioritization; scope adjustment if needed |
| RSK-P03 | Integration Complexity | Components harder to integrate than expected | 2 | 3 | 6 | MEDIUM | Interface-first design; integration tests early; modular architecture |
| RSK-P04 | Documentation Debt | Code outpaces documentation | 3 | 2 | 6 | MEDIUM | Document-as-you-go policy; documentation reviews |

# 5. External Risks

| ID | Risk | Description | L | I | Score | Rating | Mitigation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RSK-E01 | Claude API Changes | Anthropic changes API, pricing, or terms | 2 | 4 | 8 | MEDIUM | LLM-agnostic abstraction layer; monitor announcements; budget buffer |
| RSK-E02 | Wikidata Schema Change | Source data structure changes break ETL | 2 | 2 | 4 | LOW | Abstraction layer; monitoring; versioned schemas |
| RSK-E03 | Competitive Solution | Major vendor releases similar product | 2 | 2 | 4 | LOW | NTP differentiation; open source community; speed to market |
| RSK-E04 | AI Regulation Impact | New regulations affect deployment model | 2 | 3 | 6 | MEDIUM | Audit trail supports compliance; transparent reasoning; monitor regulatory landscape |
| RSK-E05 | Open Source Adoption | Low community engagement reduces momentum | 3 | 2 | 6 | MEDIUM | LinkedIn articles; clear documentation; GitHub presence; conference talks |

# 6. Risk Summary

## 6.1 High Priority Risks (Score 12+)

| Risk ID | Risk | Score | Immediate Action |
| --- | --- | --- | --- |
| RSK-T01 | NTP Rule Complexity | 12 | Domain expert review each sprint |
| RSK-K01 | Missing Source Material | 12 | Search academic libraries; proceed with validated |
| RSK-P01 | Scope Creep | 12 | Strict change control |

## 6.2 Risk Review Schedule

• HIGH risks: Weekly review at sprint planning

• MEDIUM risks: Bi-weekly review

• LOW risks: Monthly review

• All risks: Full reassessment at phase transitions

# 6.3 Risk Ownership

| Risk Category | Owner | Risks |
| --- | --- | --- |
| Technical Risks | Development Lead | RSK-T01 through RSK-T05 |
| Knowledge Risks | Domain Expert (Andreas) | RSK-K01 through RSK-K03 |
| Project Risks | Project Manager | RSK-P01 through RSK-P04 |
| External Risks | Enterprise Architect | RSK-E01 through RSK-E05 |

— End of Document —

Version 1.0 | January 2026 | V.E.R.A. Open Source Initiative